## New Measures
Status : | Working In Progress
Description : | new measures required by Finance and Craig
File Location : | Data Warehouse Project\Change Requests
No | UpdateDate | Assignee | Action/Progress/Comments | Status | Next Action
1 | 2017-04-01 | Toni, Kam | Get all Required Measures | Done | Identify New requirements
2 | 2017-05-01 | Emma | Identify new required measures around 60 new measures | Done | Give detailed definition for each new measures
3 | 2017-05-04 | Toni, Kam, Emma | updated file with some definitions/queries | In Progress | send to Dimodelo for quotation
4 |  |  | send to Adam
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## Missing Transactions
Status : | Working In Progress
Description: | Missing Transaction Types in DW
File Location: | Data Warehouse Project\Testing\Missing TransactionType.xlsx
SubTask No | Date | Assignee | Action/Progress/Comments | Status | Next Action
1 | 2017-05-04 | Emma | get summary of No of transactions and amount for each Missing transaction | Done | Make decision if add to DW transaction type file need to consider if those missing transactions have any impact to measures DW provides
2 | 2017-05-08 | Toni | confirm with Finance | Done | Modify transaction type csv to add them with correct group
3 |  | Emma, Toni | Modify Transaction type csv
4 |  | Emma | check if formulas need to be modified
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Transaction Fact Testing
Status : | Working In Progress
Description: | Transaction Fact Testing
File Location:
SubTask No | UpdateDate | Assignee | Action/Progress/Comments | Status | Next Action
1 | 2017-05-09 | Emma | testing measures associated to transaction fact database side testing | done | give examples
2 | 2017-05-10 | Emma | examples provided to Adam | done | get feedback from Adam and conduct database side testing again
3 | 2017-05-11 | Emma, Toni | testing measures associated to transaction fact | in progress
4 | 2017-05-22 | Emma, Toni | 3 formulas need to be modified. | tickets to Adam
5 |  | Toni | transaction type csv update, regroup | done
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Snapshot Testing
Status : | Working In Progress
Description: | Snapshot Testing
File Location:
SubTask No | UpdateDate | Assignee | Action/Progress/Comments | Status | Next Action
1 | 2017-05-19 | Emma | database testing check Loan number by branch. Duplicated loans in snapshot. Ticket raised and assigned to Adam | done

## Done - Measures Formula Input
Status : | DONE
Description: | Measures are not calculated correctly. Adam send through Formulas, need to be checked and give Dimodelo advise on the issues in those formulas
File Location: | \Data Warehouse Project\Measures\Calculated measures input
No | UpdateDate | Assignee | Action/Progress/Comments | Status | Next Action
1 | 2017-05-03 | Emma | check formulas along with transaction type file | send back to Adam | meeting with Adam to walk through each measure
2 | 2017-05-08 | Emma | confirmed formulas | send to Adm Done | Dimodelo will deploy the changes
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19