## Data Warehouse Matrix
Facts | Customer | Loan | Calendar | Product | Branch | Transaction Type | Loan Status | Broker Contact | Broker | Officer | Dimension Usage Count | Complexity | Fact Estimates | Analysis | Modeling | Source Target Mapping | Build & Unit Test | With Dimodelo Estimate | Without Dimodelo Estimate
Transactions | M | 1 | 1 | 1 | 3 | 1 |  |  |  | 1 | 6 | C |  | 0.42 | 0.42 | 0.42 | 1.54 | 2.8 | 8
Periodic Daily Loan Snapshot | M | 1 | 1 | 1 | 3 |  | 1 | 1 | 1 | 1 | 8 | HC |  | 0.63 | 0.63 | 0.63 | 2.31 | 4.2 | 12
Accumulating Loan Snapshot | M | 1 | 8 | 1 | 3 |  |  | 1 | 1 | 6 | 5 | HC |  | 0.63 | 0.63 | 0.63 | 2.31 | 4.2 | 12
Reference | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 6 | C |  | 0.42 | 0.42 | 0.42 | 1.54 | 2.8 | 8
Fact Usage Count | 1 | 4 | 3 | 4 | 1 | 2 | 1 | 2 | 2 | 2 |  |  |  | 2.1 | 2.1 | 2.1 | 7.7 | 14 | 40
Complexity | HC | HC | C | C | C | C | C | S | S | HC
Dimension Estimates
Analysis | 0.63 | 0.63 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.15 | 0.15 | 0.63 | 4.29
Modeling | 0.63 | 0.63 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.15 | 0.15 | 0.63 | 4.29
Source Target Mapping | 0.63 | 0.63 | 0.42 | 0.42 | 0.42 | 0.42 | 0.42 | 0.15 | 0.15 | 0.63 | 4.29 | [6 empty] | With Dimodelo - Total Days | 42.6
Build & Unit Test | 2.31 | 2.31 | 1.54 | 1.54 | 1.54 | 1.54 | 1.54 | 0.55 | 0.55 | 2.31 | 15.73 |  |  |  | vs
With Dimodelo Estimate | 4.2 | 4.2 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 1 | 1 | 4.2 | 28.6 | [6 empty] | Without Dimodelo - Total Days | 122
Without Dimodelo Estimate | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 3 | 3 | 12 | 82
contact@dimodelo.com
© Dimodelo Solutions 2016. See www.dimodelo.com for terms of use.

## Project Work Breakdown
Typical Work Breakdown |  | Without Dimodelo |  |  | With Dimodelo
| Days | Rate | $ | Days | Rate | $ | Notes
Analysis
Business Analysis | 4 | 1350 | 5400 | 4 | 1350 | 5400 | Investigate requirements, business processes, sources.
High Level Design | 2 | 1350 | 2700 | 2 | 1350 | 2700 | Develop a high level design for the DW.
Handover | 2 | 1350 | 2700 | 2 | 1350 | 2700 | Handover from M3 to Dimodelo. Handover to developer.
PreRequisites
Establish Development Environment | 2 | 1350 | 2700 | 2 | 1350 | 2700 | Establish Connectivity, Logins, Source Control, Development copies of databases etc
Establish Test Environment | 0 | 1350 | 0 | 0 | 1350 | 0
Build and Unit Test
Data Warehouse
Dimensions | 82 | 1100 | 90200 | 28.6 | 1100 | 31460
Facts | 40 | 1100 | 44000 | 14 | 1100 | 15400 | Dimodelo Architect Savings: $87,340
Cube/Tablular Model | 11 | 1100 | 12100 | 11 | 1100 | 12100 | Including any calculated Measures
Manual Data Entry | 4 | 1100 | 4400 | 4 | 1100 | 4400 | Master Data Services. Setup MDS
System/UAT Testing | 5 | 1100 | 5500 | 5 | 1100 | 5500 | This represents time required to respond to issues found in Testing
Deployment | 5 | 1100 | 5500 | 5 | 1100 | 5500 | Several Deployments over course of project, including TEST and PROD.
Security | 2 | 1100 | 2200 | 2 | 1100 | 2200 | Implement data security.
Project Management | 4 | 1350 | 5400 | 4 | 1350 | 5400 | Time for reporting status, communication, management.
Documentation & Handover | 3 | 1350 | 4050 | 3 | 1350 | 4050 | Solution documentation and handover to M3 if required.
Without Dimodelo Architect Total | 166 |  | 186850 | 86.6 |  | 99510
contact@dimodelo.com
© Dimodelo Solutions 2016. See www.dimodelo.com for terms of use.

## Variables
Estimates
Use the table below to assign a number of days to each of the complexity options available in the Data Warehouse matrix. Use a With and Without Dimodelo Architect value. Our experience is that Dimodelo Architect saves around 65% of the build time.
Complexity Code | Complexity Name | With Dimodelo Estimate (Days) | Without Dimodelo Estimate (Days) | Description
S | Simple | 1 | 3 | A Simple Dimension or Fact is source from a single existing source, with mostly a one to one relationship between source columns and destination columns. The Source is readily available and accessible.
M | Medium | 1.75 | 5 | A Medium Dimension or Fact is source from a single existing source, with mostly a one to one relationship between source columns and destination columns. However the source many need to be created, purely for reporting purposes, or there may be many attributes or measures.
C | Complex | 2.8 | 8 | Complex will involves at least one issues like: the Source is undecided, data quality issues, multiple sources, many attributes, many measures, many dimension associations, or there are complex transformations and/or derived staging tables required to derive measures or attributes.
HC | Highly Complex | 4.2 | 12 | Highly Complex will involve a combination of a number of issues like: the Source is undecided, data quality issues, multiple sources, many attributes, many measures, many dimension associations, or there are complex transformations and/or derived staging tables required to derive measures or attributes.
Task Breakdown
Use the table below to breakdown the work required for each Fact and Dimension into Analysis, Modelling, Source-Target mapping and Build/Unit Testing tasks. The braekdown is used in the Data Warehouse Matrix spreadsheet to break down all work over these task categories.
Task | Breakdown
Analysis | 15%
Modeling | 15%
Source Target Mapping | 15%
Build & Unit Test, Integrate | 55%
Variables
Daily Rate | 1350
Entity Type
Dimension
Fact
contact@dimodelo.com
© Dimodelo Solutions 2016. See www.dimodelo.com for terms of use.
Note on C22: agilmore: Set the daily rate of labour on the project This is isn't just annual salary/number of work days in a year (approx 200). This usually includes an overhead for providing the workplace and all other costs associated with employment.

## Accumulated Loan Snapshot Fact
Good to go | No Need anymore | need to be confirmed | Missing, need to be decided | New
Name: | Accumulating Loan Snapshot
Type: | Fact
Description: | An accumulating snapshot of loans. One row per Loan including Applications. This fact captures the progression of a loan through its statuses (Application, settlement, discharge, doubtful etc). The measures can be analysed by the periods in which the loan entered each status.E.g Sum of Cash Out for all Loans where the Customer is a New Customers and the loan is Settled in July 2016.
Measures: | Name | Description |  |  | Data Profiling | Format | Calculated | Data Profiling 2 | Questions ? | Source in Staging Database
| Application Amount | Amount Customer applied for. | [5 empty] | from io_product_controlbalance where RCB_IDLink_XRBl='{f6e26460-bf66-40fd-9bb2-112ebc2f2b07}' |  | ControlBalance.LoanApplication
| Cash Out | Actual Amount dispersed to Customer on settlement (excluding broker payments, insurance etc). There can be multiple disbursements for a single loan. Only includes original Disbursement amounts, not follow on disbursements at a later date. |  |  | [New Loan Application Amount] From io_product_controlbalance | $ |  | under TransactionGroup CashOut, TypeGroup Disbursement -subGroup Disbursement - subGroup Cash disbursement-$50 Data in control balance table is reliable, from io_product_controlbalance where RCB_IDLink_XRBl='{fa9b4019-3380-435c-bcdd-40b78d39471e}' | RCB_IDLink_XRBl='{fa9b4019-3380-435c-bcdd-40b78d39471e}' = "Loan\Standard\New Application Amount" in io_Control_ProductBalance | ControlBalance.NewApplicationAmount
| Commission (new) | [6 empty] | TransactionTypeGroup as 'Commission' |  | A new calculated measure on this fact table that sums transaction DebitlessCredit where TransactionTypeGroup is Commission.
| Insuance (new) | [6 empty] | TransactionTypeGroup as 'Insurance' |  | A new calculated measure on this fact table that sums transaction DebitlessCredit where TransactionTypeGroup is Insurance.
| Est monthly account fees (for entire loan) | Estimated total of Monthly account fees over the life of the loan |  |  | Total fees from the DSS tables | $ |  |  | Contractual amount at start of loan. Won't change over time. Which Column ? | DataStorage_SalesReport.DSS_MonthlyServiceFee
| Est interest (for entire loan) | Estimated total of interest over the life of the loan |  |  | Total estimated interest from the DSS table | $ |  |  |  | DataStorage_SalesReport.DSS_TotalInterest
| Gross Bad Debt | Principal balance from when the loan went bad. (loan status change to '%collection%') |  |  |  | $ |  |  | Date the loan went to collections io_status_master_reference (from to status), | This will need to wait until the periodic snapshot is available.
| Income | Combined Income of Loan Applicants |  |  |  | $ |  | See LoanIncomeQuery | Missing data on loans. If a loan doesn't have income and expenses, go to the income and expenses for the customers and apply it to the loan. Is this monthly, annual etc | Income.MonthlyIncome
| Expenses | Combined Expenses of Loan Applicants |  |  |  | $ |  | See LoanExpensesQuery | Is this monthly, annual etc | Expense.MonthlyExpense
| Approval Duration (Days) | Days between Application and Approval |  |  |  | #
| Decline Duration (Days) | Days between Application and Decline |  |  |  | # |  |  |  | Days difference between Lodgement Date and Decline date.
| Doubtful Duration (Days) | Days between Settlement and Doubtful |  |  |  | # |  |  |  | Not required
| Bad Debt Duration (Days) | Days between Settlement and Bad Debt (loan status change to '%collection%') |  |  |  | # |  |  | iO_Status_MasterReference | Days difference between Settlement Date and Decline date.
| Settlement Duration (Days) | Days between Application and Settlement |  |  |  | # |  |  |  | Days difference between Lodgement Date and Settlement date.
| NAF | Net Amount Financed. Cash Out Amt + Brokerage + Insurance. |  |  | Brokerage and Insurance from the transaction table | $ |  | see NAF-Defination doc | Brokerage and Insurance from the transaction table | This already exists on the Transaction Fact. Move to this Fact.
| Zero Balance Duration | Days between Settlement and Zero balance |  |  |  | # |  |  | zero balance comes from transactions | Can't do this until preiodic snapshot is done.
| Discharge Duration (Days) | Days between Settlement and Discharge |  |  |  | # |  |  |  | Days difference between Settlement Date and Discharge date.
Measures on top of above | Average Cash Out Amount | Cash Out amount divided by number of successful (settled) loans |  |  |  | $ | Y | Should this be amount. Is amount Cash Out ? Yes | For Loans settled in a calendar period, return average cash out amount | For Loans settled in a settled calendar period (i.e. user selects a calendar period from Settlement calendar), return average cash out amount
| New Customer Average Loan Amount | Loans where the customer hasn't had a loan previously ? Yes |  |  |  | $ | Y | New Customer, the loan is the customer's first loan (exclude Cheque Cashing). |  | Where Loan Dimension.New Customer = "New Customer", return Average "Cash Out" Amount ("Cash Out" measure on this fact table).
| Existing Customer Loan Amount | Loans where the customer has had a loan previously |  |  |  | $ | Y |  |  | Where Loan Dimension.New Customer = "Existing Customer", return Average "Cash Out" Amount ("Cash Out" measure on this fact table).
| Settled Loan Count | Count of all settled loans |  |  |  | # | Y |  |  | For Loans settled in a settled calendar period, return count of loans (rows).
| New Customer Settled Loan Count | Count of Loans where the customer hasn't had a loan previously |  |  |  | # | Y |  | Is this name too long for powerBI? Does PowerBI wrap column names. Potentially 'New Cust Settled Loan #' | For Loans settled in a settled calendar period (i.e. user selects a calendar period from Settlement calendar), and Loan Dimension.New Customer = "New Customer" return count of loans (rows).
| Existing Customer Settled Loan Count | Count of Loans where the customer has had a loan previously |  |  |  | # | Y |  |  | For Loans settled in a settled calendar period (i.e. user selects a calendar period from Settlement calendar), and Loan Dimension.New Customer = "Existing Customer" return count of loans (rows).
| New Customer Loans # v. Total Customers # |  |  |  |  | % | Y |  | % based on amount or count ? | (Where Loan Dimension.New Customer = "New Customer", return Loan Count)/(Where Loan Dimension.New Customer = "Existing Customer", return Loan Count)
| Declined Loans Count - New Customers | Number of loans declined where the customer hasn't previously had a loan |  |  |  | # | Y |  |  | For Loans declined in a declined calendar period (i.e. user selects a calendar period from declined calendar), and Loan Dimension.New Customer = "New Customer" return count of loans (rows).
| Declined Loans Count - Existing Customers | Number of loans declined where the customer has previously had a loan |  |  |  | # | Y |  |  | For Loans declined in a declined calendar period (i.e. user selects a calendar period from declined calendar), and Loan Dimension.New Customer = "Existing Customer" return count of loans (rows).
| Declined Loans Count | Count of all declined customers |  |  |  | # | Y |  | Do you mean count of declined loans yes | For Loans declined in a declined calendar period (i.e. user selects a calendar period from declined calendar), return count of loans (rows).
| Total Declined Loans vs. Total Loans | Total loans divided by Declined loans |  |  |  | % | Y |  | Should this be Declined loans divided by Total loans yes | "Declined Loans Count"/Loans Count
Relationships: | Dimension Name | Role Play |  |  | Description | Data Profiling
| Customer | Primary Customer |  |  | Primary associated Customer
Loan
Product
Broker (new)
Broker Contact
| Calendar | Application Date
| Calendar | Approved Date
| Calendar | Settlement Date
| Calendar | Discharge Date
| Calendar | First Payment Date
| Calendar | Last Payment Date
| Calendar | Bad Debt Date
| Calendar | Doubtful Debt Date
| Calendar | Declined Date
| Officer | Lending Team
| Officer | Assessor
| Officer | Data Entry Clerk
| Officer | Approval Officer
| Officer (new) | Collection Officer | [5 empty] | iO_Control_LinkMaster where XLK_ID='{d497b5f6-afd4-451a-81c6-fd82d8f09d0a}'
| Officer | Settlement Officer
| Branch | Lender Branch |  |  | Same as Settlement Branch
| Branch | Contact Branch |  |  | Branch associated with very first transaction with Customer.
| Branch | Settlement Branch |  |  | Where money was distributed from (i.e. Associated Branch when the first time status group = active)
| Branch (New) | Referring Branch
| Branch | Current Branch |  |  | Branch associated with the latest transaction.
Profiling:
SELECT PMR.RMR_ID LoanPK ,xrb.xrbl_detail LoanType ,rcb_currentvalue CurrentValue FROM stg.APL_Product_ControlBalance rcb(NOLOCK) INNER JOIN stg.APL_Control_ProductBalance xrb(NOLOCK) ON rcb.rcb_idlink_xrbl = xrb.xrbl_id INNER JOIN stg.APL_Product_MasterReference PMR(NOLOCK) ON RCB.rcb_idlink_rmr = PMR.rmr_id
Data comes from Raw staging tables (above) then View/SubjectArea/ControlBalance then CB_ Prefixed views in Staging/View/Loan in Solution.
Combined with Staging/Staging/DataStorage_SalesReport. Duplicates loans can exist in this table. For any given laon is the most recent version is the valid version. Use sequence number as the delta extract key, and use loan Id as business key.
View/SubjectArea/Loan contains one row per loan including dates for Calendar associations.
Dylan: After looking at the control balance table it looks like only the LoanApplication and NewApplicationAmount (loan disbursement amount) are reliable. I wouldn’t recommend using the other measures.
Refactor: | Major refactoring required to break up snapshot and periodic snapshot.
Missing | Loan Status
Loan Term
Payment Frequency
Fees, eg application fee, establish fee, ..
Received
dishonoured
arrears
ageing
Remian Term
IntRate
TotalInterest
OstdBalance
Principal Balance
Opening Balance
dishonour count
…..

## Periodic Loan Snapshot Fact
Name: | Periodic Loan Snapshot
Type: | Fact
Description: | A Daily snapshot of all Loans including Applications. This fact is used to understand the current state of the 'loan book' on any given day. E.g Total outstanding balances as at 10 Jul 2016, where the status is doubtful, and branch is toowoomba.
Measures: | Name | Description | Data Profiling | Format | Calculated
| Loan Aging | Calculating in Ageing spreadsheet. |  | ? |  | Needs definition
Bad Debt Ageing
| $ outstanding | Sum of Loan Balance | (sum of DR - CR in Transactions, where additive) | $ |  | Alternatives, Loan Book, Loan Balance, Trade debtors.
| Unearned income |  |  | $ |  | What is the definition of this
| Defferred Revenue |  | This is in APL |  |  | Ning knows definition.
| Cash In Since Bad Debt | Sum of the cash in since the loan went bad | Sums of DRs and CRs where date > bad debt date. | $
| Cash In Since Doubtful Debt | Sum of the cash in since the loan into a status of doubtful | Sums of DRs and CRs where date > doubtful debt date. | $
| Days since last successful payment | Days since last successful payment |  | #
Relationships: | Name | Role Play | Description | Data Profiling
| Customer | Primary Customer | Primary associated Customer
Loan
Product
Loan Status
Broker
Broker Contact
| Calendar | As At Date
| Calendar | Last Payment Date
Officer Role Plays
| Branch | Contact Branch | Branch associated with very first transaction with Customer.
| Branch | Settlement Branch | Where money was distributed from (i.e. Associated Branch when the first time status group = active)
| Branch | Current Branch | Branch associated with the latest transaction.
Profiling:
Each individual loan exists in Product_ControlBalance and Product_Master reference, or DataStorage_SalesReport. See the Staging/View/SubjectArea/ControlBalance or Loan.
The definition of Aging, $ outstanding and unearned income are yet to be determined. Its likely these are calculated from Transactions.
Refactor: | Major refactoring required to break up snapshot and periodic snapshot.

## Transaction Fact
Name: | Transaction Fact
Type: | Fact
Description: | This fact contains every loan transaction. It can answer questions like, total collected fees for Customers in NSW for the month of May 2016.
Measures: | Name | Description | Data Profiling | Format | Calculated
| Debit Amt | As per source |  | $
| Credit Amt | As per source |  | $
| Total Amt | Debit Amt - Credit Amount | Increases are positive, Decreases are negative. | $
| Is Ghost | 1 if the transaction is marked as a ghost transaction |  | bit
| Is Reversal | 1 if the transaction is marked as a reversal transaction |  | bit
| Application Fee | Sum of Debit minus credit from the transactions where the transaction type is Application Fee |  | $ | Y
| Additional Monthly Fees | Sum of Debit minus credit from the transactions where the transaction type is Additional Monthly Fees |  | $ | Y
| Dishonour Fee | Sum of Debit minus credit from the transactions where the transaction type is Dishonour Fee |  | $ | Y
| Monthly Fee | Sum of Debit minus credit from the transactions where the transaction type is Monthly Fee |  | $ | Y
| Establishment Fee | Sum of Debit minus credit from the transactions where the transaction type is Establishment Fee |  | $ | Y
| Credit Fee | Sum of Debit minus credit from the transactions where the transaction type is Credit Fee |  | $ | Y
| Default Fee | Sum of Debit minus credit from the transactions where the transaction type is Default Fee |  | $ | Y
| ERD Discount | Sum of Debit minus credit from the transactions where the transaction type is ERD Discount |  | $ | Y
| Insurance out | Sum of Debit minus credit from the transactions where the transaction group is Insurance out |  | $ | Y
| Broker fee | Sum of Debit minus credit from the transactions where the transaction group is Broker fee |  | $ | Y
| Total NAF (net amount financed) | Sum of Debit minus credit from the transactions where the Loan dispersed amount plus brokerage and insurance |  | $ | Y
| No of loans | Count of dispersed loans (Disbursement flag on transaction, or transaction type) | Have a flag for disbursment transaction | # | Y | What does this mean. Should this be accumulated snapshot.
| Cash In via Direct Debit | Total cash in where the payment type was Direct debit (Payment method is in the transaction type file) |  | $ | Y
| Cash In via Cash Payment | Total cash in where the payment type was cash |  | $ | Y
| Cash In (total) | Total Cash In |  | $ | Y
| Dishonours | Count of dishonoured payments (Dishonour transaction type) |  | # | Y
| Number of payments | Count of all payments |  | # | Y
| Number of Successful Payments | Count of all successful payments |  | # | Y
| Percentage of Successful Payments | Amount of successful payments devided by payments |  | # | Y
| Is New Customer Flag | Potentially |  | bit | Y
Relationships: | Name | Role Play | Description | Data Profiling
| Customer | Primary Customer | Primary associated Customer
Loan
Product
Trasnaction Type
Calendar
Officer
| Branch | Lender Branch | Same as Settlement Branch
| Branch | Contact Branch | Branch associated with very first transaction with Customer. |  |  | Need to persist the branch at the time of the transaction, to determine what branch was Contact/Settlement/Current.
| Branch | Settlement Branch | Where money was distributed from (i.e. Associated Branch when the first time status group = active).
| Branch | Current Branch | Branch associated with the latest transaction.
Profiling:
SELECT PMR.RMR_ID LoanPK ,xrb.xrbl_detail LoanType ,rcb_currentvalue CurrentValue FROM stg.APL_Product_ControlBalance rcb(NOLOCK) INNER JOIN stg.APL_Control_ProductBalance xrb(NOLOCK) ON rcb.rcb_idlink_xrbl = xrb.xrbl_id INNER JOIN stg.APL_Product_MasterReference PMR(NOLOCK) ON RCB.rcb_idlink_rmr = PMR.rmr_id
Data comes from Raw staging tables (above) then View/SubjectArea/ControlBalance then CB_ Prefixed views in Staging/View/Loan in Solution.
Combined with Staging/Staging/DataStorage_SalesReport
View/SubjectArea/Loan contains one row per loan including dates for Calendar associations.
Dylan: After looking at the control balance table it looks like only the LoanApplication and NewApplicationAmount (loan disbursement amount) are reliable. I wouldn’t recommend using the other measures.
Refactor: | Major refactoring required to break up snapshot and periodic snapshot.

## Customer
Name: | Customer
Type: | Dimension
Description: | The person who has applied for and been granted a loan (or has been rejected). On a loan there is one primary Customer and potentially multiple secondary borrowers.
Important Attributes: | Name | Description | Data Profiling | Change
| Address | Current (most recent address) | Get latest by sequence number. See base queries - Customer Address | type 2
| Employment | Customers Current Employment Status. | See base queries - Employment | type 2
Profiling: | Customer
See Existing dimension.
Master Data:
Refactor: | Make Address and Employment type 2
Dylan: Lots of duplicated Customers. Dylan suggested Melissa Data.

## Loan
Name: | Loan
Type: | Dimension
Description: | Represents one row per Loan including Applications.
Important Attributes: | Name | Description | Data Profiling | Change
| LoanId | As per Source
| Is New Customer | Indicates the Loan is for a new Customer or Existing Customer. Values 'New Customer', 'Existing Customer'
| Loan Purpose | As per source
| PurposeExplanation | As per source
| Frequency | As per source
| Secured | Is the loan secured by collateral or not
| LoanTermMonth | As per source
Profiling:
See Existing dimension.
Refactor:

## Calendar
Name: | Calendar
Type: | Dimension
Description: | Represents all calendar periods associated with a date, including Days, Day of Week, Week, Month, Quarter, Year, Fiscal Month, Fiscal Quarter, Fiscal Year and many more. In addition - Relative periods like MTD, YTD, FYTD, Same Month last Year, Same Quarter last year, Previous year etc.
Profiling:
See Existing dimension.
Refactor:

## Product
Name: | Product
Type: | Dimension
Description: | Represents one row per Loan Type.
Important Attributes: | Name | Description | Data Profiling | Change
| Product | As per Source
| Product Short Name | As Per Source
| Min Loan | Minimum Loan Amount for this Product Type.
| Max Loan | Maximum Loan Amount for this Product Type.
| Min Term | Minimum Loan Term for this Product Type.
| Max Term | Maximum Loan Term for this Product Type.
Profiling:
See Existing dimension.
Refactor:

## Branch
Name: | Branch
Type: | Dimension
Description: | Money 3 have a Branch network who provide Loans to Customers. When associated with Loans a Branch is defined as either the Lender, Settlement, Current or First Contact Branch.
Important Attributes: | Name | Description | Data Profiling | Change
| BranchCompany | As per Source
| BranchGroup | As per Source
| BranchCountry | As per Source
| BranchEntity | There used to be Franchises as the Owning Entity.
| BranchStateCode | As per Source
| BranchSubGroupState | As per Source
| BranchAreaCode | As per Source
| BranchArea | As per Source
| Branch | As per Source
| ABN | As per Source
| ACL | As per Source
| Shop | As per Source
| Street | As per Source
| Suburb | As per Source
| PostCode | As per Source
| Fax | As per Source
| Phone | As per Source
Profiling:
See Existing dimension. The source of this a Master Data CSV.
Refactor: | The Source of this table comes from Master data CSV. This needs to be converted into Master Data Services.

## Transaction Type
Name: | Transaction Type
Type: | Dimension
Description: | Classification of Transaction Types into Groups and Sub Groups. In additon trasactions are classified as reversals, additive and associated with GL Accounts. E.g Application Fee. A Transaction Type can be a charge or a reversal, both the charge and reversal should share the same name, but a reversal has an indicator to identify it as a reversal. Additive transaction types affect the Loan Balance, while Non Additive Transaction Types don't affect the balance. Another way to define additive transaction is additive trasnasctions have a related GL Account. Examples of Non Additive transaction Type ($50 for Free promotion, extra $50 on their loan.. essentially a gift). Transactions can be Ghosted or Non Ghosted. If a transaction is Ghosted, the user can't see it. It may be some internal adjustment.
Important Attributes: | Name | Description | Data Profiling | Change
| TransactionTypeID | As per Source
| Transaction | As per Source
| TransactionCompany | As per Source
| TransactionGroup | As per Source
| TransactionTypeGroup | As per Source
| TransactionTypeSubGroup | As per Source
| TransactionName | As per Source
| Additive | Additive transaction types affect the Loan Balance, while Non Additive Transaction Types don't affect the balance.
| Is Reversal | Identifies this transaction type as a reversal.
| Is Ghost | Indicates this Transction Type represents a Ghost Transaction | Join the list of transactions to a two row derived table with members 'Is Ghost', 'Is Not Ghost' to get a Ghosted and Non Ghost version of every Transaction Type.
| GL_CR_Account | As per Source
| GL_DB_Account | As per Source
Profiling:
See Existing dimension. The source of this a master data CSV
Refactor: | The Source of this table comes from Master data CSV. This needs to be converted into Master Data Services?
Need to modify CSV to take reversal out of transaction name, add a reversal coulmn and add a payment method column

## Loan Status
Name: | Loan Status
Type: | Dimension
Description: | Loan Statuses categorized into groups.
Important Attributes: | Name | Description | Data Profiling | Change
| StatusDetail | As per Source
| StatusShortName | As per Source
| StatusGroup | As per Source
Profiling:
See Existing dimension. The source of this hard coded query.
Refactor: | The Source of this table is a hard coded query. This needs to be converted into Master Data Services.

## Broker
Name: | Broker
Type: | Dimension
Description: | Broker is an external Broker Organsiation (e.g. Rapid Finance, Stratten Finance) who brokered the Loan.
Important Attributes: | Name | Description | Data Profiling | Change
| Broker Name | As per Source | Broker Contact
Profiling:
See Existing dimension.
Refactor:

## Broker Contact
Name: | Broker Contact
Type: | Dimension
Description: | Broker Contact is the person at the external Broker Organsiation (e.g. Rapid Finance, Stratten Finance) who brokered the Loan. Broker Contacts can be associated with more than one Broker.
Important Attributes: | Name | Description | Data Profiling | Change
| Broker Contact Name | As per Source | Broker Contact
Profiling:
See Existing dimension.
Refactor:

## Officer
Name: | Officer
Type: | Dimension
Description: | An Employee within the Money3 organisation. Offiicers take on a variety of roles in the organisation including Approval, Assessor, DataEntry Clerk, LendingTeam, Settlement Officer etc.
Important Attributes: | Name | Description | Data Profiling | Change
| Name | As per Source
Profiling:
See Existing Dimensions. The Dimensions are currently broken up into separate dimensions for Approval Officer, Assesor etc. Has dirty data in it though… SELECT DISTINCT CMR_Officer.CMR_Name Officer FROM IO_Client_MasterReference CMR_Officer(NOLOCK) LEFT JOIN IO_Link_MasterReference LMR_Officer(NOLOCK) ON LMR_Officer.LMR_IDLink_CMR = CMR_Officer.CMR_ID WHERE LMR_Officer.LMR_IDLink_Association IN( '{f53c875d-63b6-454e-a58e-d7cec8fc247c}' --LendingTeam ,'{89517398-1927-4eb5-868e-640ed00bc956}' -- SettlementOfficer ,'{299646a4-d179-43c9-8fb0-4ac1af1d45b8}' -- ApprovalOfficer ,'{d8dcb018-54c1-4ba3-8b28-66973a09dc45}' )-- Assessor AND COALESCE(LMR_Officer.lmr_idlink_code_id, '') ! = '' AND COALESCE(CMR_Officer.CMR_Name, '') ! = ''
Refactor: | Consolidate the various dimensions into a single dimension and create role plays on the fact.

## Master Data
Branches
TransactionTypes
Statuses

## Sources
M3_MAIN
Table | Represents | Abbreviation
io_Product_Transaction | Loan Transactions | RTM
io_Link_MasterReference | Represents a link between Product Master Reference (Loan) and Client Master Reference (Client/Person/Branch etc). Contains Loan Id, Client Id and Association type Id. Look at Association Type dimension in Warehouse, and Reference fact. There are duplicates in this table over business key - Loan, Client, and association type. | LMR
io_Product_MasterReference | Loan | RMR
io_Link_AssociationHistory | Not sure , history of Client to Product association | LAH | May be useful for Branch history
io_Client_masterReference
io_Control_ProductMaster | Products
Client_MasterReference | Clients, Branches,People
Control_LinkMaster | has name of association type. For link master reference.
20
160
480